## Pillars of Success
The Entrusted Mitigation Plan
Establish a clear plan on install. All points must be completed for install to be complete. Create it, Communcate it, Crush the plan.
TRUE | Day 1 | [5 empty] | FALSE | Day 8
[5 empty] | VIP: | FALSE
TRUE | I | Notes: |  |  |  |  | FALSE | I | Notes:
FALSE | Pr |  | Cause of Loss: |  |  |  | FALSE | Pr
FALSE | D |  | Pinhole copper pipe leak in wall |  |  |  | FALSE | D
FALSE | CS | [5 empty] | FALSE | CS
FALSE | Pu |  | Specific Demo & Critical Job related Instructions: |  |  |  | FALSE | Pu
FALSE | Day 2 |  | Send someone who speaks Spanish to explain in detail what is going on. If we end up demoing the cabinetry, it’s a 2 man job. Living room: check the marked drywall behind the table. I pulled the baseboard and didn’t find growth, so we should be able to dry in place. Dining room: there is growth present inside the hole cut by the plumbers. There was also growth present along the baseboard I pulled. Get confirmation from HO and ML that we are good to flood cut that area. Kitchen: the cabinetry is saturated. The sink will need to be capped before we can demo. It’s tower hill insurance, so see with ML if it’s something we should wait to do during rebuild. |  |  |  | FALSE | Day 9
FALSE | I | Notes: |  |  |  |  | FALSE | I | Notes:
TRUE | Pr | [5 empty] | FALSE | Pr
FALSE | D | [5 empty] | FALSE | D
FALSE | CS | [5 empty] | FALSE | CS
FALSE | Pu | [5 empty] | FALSE | Pu
FALSE | Day 3 | [5 empty] | FALSE | Day 10
FALSE | I | Notes: |  |  |  |  | FALSE | I | Notes:
FALSE | Pr |  | Total Equipment needs after install: |  |  |  | FALSE | Pr
FALSE | D |  | N/A |  |  |  | FALSE | D
FALSE | CS | [5 empty] | FALSE | CS
FALSE | Pu | [5 empty] | FALSE | Pu
FALSE | Day 4 |  | Debris Plan: | Van/Truck Haul | Bag Dumpster | Large Dumpster | FALSE | Day 11
|  |  | select all that apply | TRUE | FALSE | FALSE
FALSE | I | Notes: |  |  |  |  | FALSE | I | Notes:
FALSE | Pr | [5 empty] | FALSE | Pr
FALSE | D |  | Job Site ready for demo plan and contents are not an issue: |  | Yes, Demo Ready | No, See below | FALSE | D
FALSE | CS |  |  |  | FALSE | TRUE | FALSE | CS
FALSE | Pu |  | Sink needs to be capped |  |  |  | FALSE | Pu
FALSE | Day 5 | [5 empty] | FALSE | Day 12
FALSE | I | Notes: | Customer's availability for job timeline / special requests / potential issues: |  |  |  | FALSE | I | Notes:
FALSE | Pr |  | Language barrier. Send Spanish speaker |  |  |  | FALSE | Pr
FALSE | D | [5 empty] | FALSE | D
FALSE | CS | [5 empty] | FALSE | CS
FALSE | Pu |  | Subs Required: | Include: Date, Time, Who is hired, customer confirmation etc. |  |  | FALSE | Pu
FALSE | Day 6 |  | Plumbing: | TRUE |  |  | FALSE | Day 13
FALSE | I | Notes: | Countertops: | FALSE |  |  | FALSE | I | Notes:
FALSE | Pr | [5 empty] | FALSE | Pr
FALSE | D |  | Labor Crew: | FALSE |  |  | FALSE | D
FALSE | CS | [5 empty] | FALSE | CS
FALSE | Pu |  | Other: | FALSE |  |  | FALSE | Pu
FALSE | Day 7 | [5 empty] | FALSE | Day 14
FALSE | I | Notes: |  |  |  |  | FALSE | I | Notes:
FALSE | Pr |  | Field Supervisor Notes: |  |  |  | FALSE | Pr
FALSE | D | [5 empty] | FALSE | D
FALSE | CS | [5 empty] | FALSE | CS
FALSE | Pu | [5 empty] | FALSE | Pu